## Slide 1: Evaluating Programs to Combat Violence Against Women and Children
RAND Corporation

## Slide 2: Non-partisan, objective research and analysis
Goals:
Site Summaries
Process Evaluation
Outcome Evaluation

## Slide 3: Everyone will have a role in parts of the evaluation
What are we doing?
  Summaries of each site’s program design
  Implementation process evaluation
  Designing data collection plans for measurement and evaluation
  Conducting a “deeper dive” outcome evaluation with some providers
Who participates?
  All providers participate in initial assessment
  All providers can contribute their expertise to understanding programs, outcomes, findings, etc.
  Some selected for more in-depth evaluation

## Slide 4: Implementation process evaluation asks two main questions:
  Did programs follow planned program logic?
    If not, why were changes necessary?
  What were the challenges, successes, and adaptive strategies?
Program Design
Challenges and Barriers
Program Operations
Major
Components

## Slide 5: Process evaluations help us understand the program
Why conduct a process evaluation?
  Understand what was actually implemented
  Understand what outcomes might be expected
  Highlight new and innovative practices to a broader community
  Process evaluation work has started already
  All programs will be part of some aspects of the process evaluation
  Discussions with RAND about program activities, timeline, changes to program plans, expected client numbers
  Background learning: client population, communities’ cultures, current and historical contexts
  Development, revision of logic models

## Slide 6: Outcome evaluation asks three main questions:
  Can the program activities be quantified, measured?
  How can we measure the changes in which we are interested?
  What was the effect of the program on the changes we measured?
Program Outputs
Observed Changes
Data Collection
Major
Components

## Slide 7: All providers will participate in initial assessment, others in full evaluation
Initial assessment
Process evaluation
Who: All providers
What: Program summary highlighting major components
When: Now until April 2018
How: Phone calls and in-person site visits with RAND
Full evaluation
Who: Selected providers TBD
What: Most rigorous evaluation design possible to assess impact of program
When: January 2018 until September 2019
How: Phone calls and in-person site visits with RAND, surveys, other data collection where possible

## Slide 8: Data to be collected is still being determined
Potential Quantitative Data
Staff recruitment and retention
Staff training
Clients served over time
Client attendance at events
Client referrals
Clients reporting incidents to police
Clients attending court hearings
School attendance
Child removals
Family involvement in treatment
Potential Qualitative Data
Familial perception of change in perpetrator
Self-confidence in women
Self-image in men
Conversations in the community about violence
Community engagement
Willingness to return for services
Psychological wellbeing
Inclusion of community culture in programming
Readiness for behavior change

## Slide 9: There will be minimum data requested of providers to collect
Client name
Client DOB
Client postcode
Client Indigenous status
Involvement in legal system (DVO, pending court case)
Number of clients served
Hours spent per client
Source of client referral
Services provided to client
Connection to child services

## Slide 10: RAND is undertaking a rigorous ethics process
HSPC
RAND internal
Initial approval received
AIATSIS
Australia-wide
To be completed
Local
Local to each organisation and/or community
Will be completed as needed
Ongoing oversight

## Slide 11: The evaluation is on track
Step 1: Program Design and Logic
Step 2: Detailed Review of Program
Step 3: Selection of Full Evaluation Programs for Detailed Evaluation
Step 4: Full Evaluation of Selected Programs and Presentation of Results
June 2017 – Present
Sept. 2017 – January 2018
January 2018 – March 2018
March 2018 – February 2019

## Slide 12: Where are we now?
Literature and Document Reviews
  Research on violence against women and children in Australia and elsewhere
  Review of historical and current documents on community contexts
  Identification of sources for secondary data collection
  Identification of existing measures, instruments for use with Aboriginal populations
Evaluation Design
  Initial review of potential outcomes and feasibility in different contexts
  Power analyses and review of plausible research design
Provider Communication
  Phone calls with every provider
  Site visits scheduled with KWY, Mookai Rosie, NAAFLS, NPY, VACCA, Yoowinna

## Slide 13: Where are we going next?
Evaluation Design
  Finalise outcome measures
  Write program summaries
  Identify sites for full evaluation
  Submit for full ethics approvals
Provider Communication
  Schedule phone calls for November with sites that we do not visit this month
  Engage in ongoing dialogue with all sites about data and measures

## Slide 14: QUESTIONS?